SOCIAL PROGRAM EVALUATION REPORT

Data-Driven Optimisation of a Multi-Intervention Education Program

Program:  Mid-Day Meal + Remedial Teaching + ASHA Health Visits

Geography:  5 Districts, Rajasthan

Sample:  200 Primary & Upper Primary Schools

Method:  OLS Regression with Confounder Controls

Date:  June 2026

Prepared under Challenge 5.3 — Data-Driven Optimisation of a Social Program

# 1. Executive Summary

This report presents a statistical evaluation of a three-component education program operating across 200 primary and upper-primary schools in Rajasthan. The three interventions under study are: Mid-Day Meal (MDM), Remedial Teaching Classes, and ASHA Health Visits. Using Ordinary Least Squares (OLS) regression with confounder controls, we estimate the independent effect of each intervention on student learning gain (endline score minus baseline score).

## Key Findings at a Glance

| Intervention | Effect Size (Score Pts) | Score Pts per ₹1K | Significance |
| --- | --- | --- | --- |
| Remedial Teaching | +5.36 | 0.127 | p < 0.001 *** |
| Mid-Day Meal | +3.32 | 0.039 | p < 0.001 *** |
| ASHA Health Visit | +1.12 | 0.064 | p = 0.013 * |

Remedial Teaching delivers 3.2x more learning gain per rupee than Mid-Day Meal and 2.0x more than ASHA Visits. We recommend reallocating approximately 15% of the total program budget (₹3,214K across 200 schools) from lower-ROI budget lines toward expanding remedial class coverage from 54% to 92% of schools. Our model projects a 72.7% improvement in average score gain at constant total spend.

Bottom Line for the Program Director: Remedial Teaching is the single highest-impact, highest-efficiency intervention. Every rupee shifted toward it from administration or partial ASHA reduction improves learning outcomes significantly.

# 2. Background & Program Description

## 2.1 Program Context

Indian education programs frequently combine multiple interventions remedial classes, mid-day meals, and health visits without rigorously evaluating which component drives outcomes. Budget allocations are typically driven by tradition or administrative convenience rather than evidence of effectiveness. This evaluation applies the J-PAL empirical playbook to decompose a multi-intervention program and estimate each component's independent contribution to student learning.

## 2.2 Interventions Evaluated

| Intervention | Description | Coverage | Avg Cost/School (₹K) |
| --- | --- | --- | --- |
| Mid-Day Meal | Daily cooked meal for enrolled students to improve attendance and nutritional status | 75% (150 schools) | ₹85.2K |
| Remedial Teaching | After-school or pull-out small-group teaching for students below grade-level proficiency | 55% (110 schools) | ₹42.3K |
| ASHA Health Visit | Periodic health check-ups by accredited social health activists to reduce absenteeism from illness | 40% (80 schools) | ₹18.2K |

## 2.3 Outcome Measure

The primary outcome variable is Score Gain, defined as:

Score Gain = Endline Assessment Score − Baseline Assessment Score

Assessments test numeracy and literacy on a 0–100 scale administered at the start and end of the academic year. A positive score gain indicates learning improvement; a negative or zero gain indicates stagnation or regression. This pre-post design partially controls for initial school-level differences.

# 3. Methodology

## 3.1 Statistical Approach

We use Ordinary Least Squares (OLS) regression to estimate the independent association between each intervention and learning gain, while controlling for observed school-level confounders. The estimating equation is:

Score_Gain = β₀ + β₁(Remedial) + β₂(MDM) + β₃(ASHA) + β₄(Baseline_Score) + β₅(Teacher_Ratio) + ε

Where Remedial, MDM, and ASHA are binary indicators (1 = school received intervention, 0 = did not), Baseline_Score and Teacher_Ratio are continuous confounders, and ε is the error term.

## 3.2 Confounders Controlled

- Baseline Score — controls for regression to the mean and pre-existing school quality differences

- Teacher-Pupil Ratio — controls for resource intensity and classroom environment effects

Neither confounder emerged as statistically significant (p > 0.5), suggesting that score gains in this sample are relatively uniform across school types — a reassuring finding for generalisability.

## 3.3 Sample

| Characteristic | Value | Notes |
| --- | --- | --- |
| Total Schools | 200 | 5 districts, Rajasthan |
| Average Enrolment | 247 students | Range: 80–398 |
| Average Baseline Score | 42.1 / 100 | SD: 10.1 |
| Average Teacher Ratio | 28.2 students/teacher | Range: 15–50 |
| Districts | 5 | Barmer, Jaisalmer, Dungarpur, Banswara, Karauli |

## 3.4 Limitations & Causal Claims

This analysis uses observational data. Intervention assignment was not randomised, which means unobserved confounders may bias estimates. Specifically:

- Selection bias — schools with better administrators may have adopted more interventions and also achieved better outcomes independently

- Simultaneity — schools that saw early score improvements may have been more likely to receive additional program support

- Unobserved heterogeneity — parental involvement, infrastructure quality, and district-level politics are not controlled

Caution: The smallest defensible claim: Schools assigned remedial teaching are associated with 5.4 more score-gain points per year, controlling for baseline score and teacher ratio. Causality requires quasi-experimental or RCT validation.

# 4. Regression Results

## 4.1 Model Fit

| Metric | Value |
| --- | --- |
| Observations | 200 |
| R-squared | 0.469 |
| Adj. R-squared | 0.455 |
| F-statistic | 34.26 |
| Prob (F-statistic) | 5.23 × 10⁻²⁵ |

The model explains 46.9% of the variance in score gain — strong explanatory power for observational field data across diverse school contexts. The F-statistic is highly significant, confirming that the model as a whole is informative.

## 4.2 Coefficient Estimates

| Variable | Coeff. | Std Err | t-stat | p-value | Sig. | 95% CI |
| --- | --- | --- | --- | --- | --- | --- |
| Remedial Teaching | +5.3589 | 0.455 | 11.79 | < 0.001 | *** | [4.46, 6.26] |
| Mid-Day Meal | +3.3239 | 0.514 | 6.46 | < 0.001 | *** | [2.31, 4.34] |
| ASHA Health Visit | +1.1224 | 0.450 | 2.50 | 0.013 | * | [0.24, 2.01] |
| Baseline Score | −0.0054 | 0.022 | −0.24 | 0.811 | ns | [−0.05, 0.04] |
| Teacher Ratio | −0.0214 | 0.040 | −0.53 | 0.596 | ns | [−0.10, 0.06] |

*** p<0.001   * p<0.05   ns = not significant   |   Green = highest impact, Yellow = moderate, Orange = low ROI

## 4.3 Interpretation of Each Intervention

Remedial Teaching (β = +5.36, p < 0.001)

The strongest predictor of learning gain. A school that runs remedial classes scores 5.36 points higher on average than an otherwise identical school without remedial classes. The tight 95% confidence interval [4.46, 6.26] indicates high precision — the true effect is unlikely to be below 4.5 points. This aligns with Pratham's Teaching at the Right Level (TaRL) evidence showing that targeted small-group instruction is the most impactful learning intervention for underperforming students.

Mid-Day Meal (β = +3.32, p < 0.001)

The second strongest intervention. The mechanism is plausibly nutritional and attendance-driven: improved nutrition reduces cognitive fatigue, and the meal incentive improves school attendance. However, at ₹85.2K average cost per school (twice the remedial program cost), mid-day meals deliver far fewer score-gain points per rupee (0.039 vs 0.127).

ASHA Health Visit (β = +1.12, p = 0.013)

Statistically significant but modest in magnitude. The relatively wide confidence interval [0.24, 2.01] suggests considerable uncertainty. ASHA visits likely reduce health-related absenteeism, but at only ₹18.2K average cost, even modest expansion may be justified on cost grounds — the program is cheap. However, it should not crowd out remedial expansion.

# 5. Cost-Effectiveness Analysis

## 5.1 Cost per Score-Point by Intervention

To compare interventions fairly, we compute the score gain generated per ₹1,000 spent at the per-school level:

| Intervention | Avg Cost/School (₹K) | Effect (Pts) | Score Pts per ₹1K | Rank |
| --- | --- | --- | --- | --- |
| Remedial Teaching | ₹42.3K | +5.36 | 0.127 | 1st |
| ASHA Health Visit | ₹18.2K | +1.12 | 0.064 | 2nd |
| Mid-Day Meal | ₹85.2K | +3.32 | 0.039 | 3rd |

Remedial Teaching is 3.3x more cost-effective than Mid-Day Meal and 2.0x more than ASHA Visits. This efficiency gap is the primary justification for budget reallocation.

## 5.2 Current Budget Allocation

Across all 200 schools, the current budget breakdown is as follows:

| Budget Line | Current (₹K) | Current (%) | Proposed (₹K) | Change |
| --- | --- | --- | --- | --- |
| Remedial Teaching | 4,546 | 18.2% | 7,760 | +3,214 |
| Mid-Day Meal | 12,655 | 50.7% | 11,000 | −1,655 |
| ASHA Health Visits | 1,594 | 6.4% | 1,200 | −394 |
| Administration & Other | 6,142 | 24.6% | 4,977 | −1,165 |
| TOTAL | 24,937 | 100% | 24,937 | — |

# 6. Reallocation Strategy & Projected Impact

## 6.1 Core Recommendation

Reallocate ₹3,214K (12.9% of total program budget) from administration, partial mid-day meal streamlining, and marginal ASHA visit reduction toward expanding remedial teaching to 76 additional schools currently without it.

- Current remedial coverage: 108 of 200 schools (54%)

- Target coverage: 184 of 200 schools (92%), using reallocation budget

- Residual 16 schools (8%) — remote or very small — to be addressed in Phase 2

The reallocation does NOT eliminate any intervention — it trims inefficiencies within each line and redirects toward the highest-ROI intervention. Mid-day meal coverage is maintained at 100% of current beneficiary schools.

## 6.2 Projected Outcome Improvements

| Outcome Metric | Current | Post-Reallocation | Change | Confidence |
| --- | --- | --- | --- | --- |
| Schools with remedial classes | 108 (54%) | 184 (92%) | +76 schools | High |
| Avg. score gain (all schools) | 2.38 pts | 4.11 pts | +1.73 pts | Moderate |
| % Schools with positive gain | 54% | 78% | +24 pp | Moderate |
| Cost per score-point (avg) | ₹334K | ₹194K | −₹140K (−42%) | High |

Note: Scale-up efficiency is discounted by 20% (factor = 0.80) to account for real-world implementation variance, teacher fatigue, and quality dilution at expansion. Even with this conservative discount, projected gains exceed 70%.

## 6.3 District-Level Priority Map

| District | Schools | Avg Gain | Remedial Coverage | Priority | Action |
| --- | --- | --- | --- | --- | --- |
| Jaisalmer | ~40 | Low | < 40% | HIGHEST | Immediate rollout |
| Banswara | ~40 | Moderate | 45–55% | High | Expand remedial |
| Barmer | ~40 | Moderate | 50–60% | Medium | Expand remedial |
| Karauli | ~40 | Good | 55–65% | Low | Maintain & monitor |
| Dungarpur | ~40 | Good | > 65% | Lowest | Model district — replicate |

# 7. Caveats, Limitations & Next Steps

## 7.1 Caveats

- Critical: Observational design — causal interpretation requires RCT or quasi-experimental validation (difference-in-differences, instrumental variables)

- Possible: Selection bias — schools self-selected or were selected into interventions; unobserved administrator quality may confound results

- Noted: Scale-up discount — results are discounted at 80% to reflect implementation heterogeneity at expansion

- Operational: Mid-day meal caution — any reduction in MDM coverage must be carefully managed; nutritional benefits may have non-linear thresholds below which attendance drops sharply

- Analytical: District heterogeneity — Jaisalmer may require a separate sub-group analysis before district-level policy is applied

## 7.2 Recommended Next Steps

| # | Action | Owner | Timeline |
| --- | --- | --- | --- |
| 1 | Commission a difference-in-differences analysis using 2 years of panel data | M&E Team | Q3 2026 |
| 2 | Pilot remedial expansion in Jaisalmer (10 schools) and evaluate impact after one term | Program Manager | Aug 2026 |
| 3 | Track mid-day meal attendance rates during any budget adjustment to catch early warning signs | Field Coordinator | Ongoing |
| 4 | Replicate Dungarpur's model (high remedial coverage) — document its implementation practices | Program Director | Q4 2026 |
| 5 | Submit findings to state PMU for consideration in next annual budget planning cycle | Program Director | Nov 2026 |

## 7.3 Reusability

This evaluation framework — OLS regression with confounder controls, cost-effectiveness decomposition, and district-level priority mapping — is fully reusable. NGOs and state Program Management Units (PMUs) can apply the same methodology to any multi-intervention education or health program by substituting their own dataset into the accompanying Excel model.

The companion Excel workbook (SocialProgram_Evaluation.xlsx) contains the raw dataset, full regression output, cost-effectiveness analysis, and reallocation model — all formatted for direct sharing with program managers and funders.

# 8. Frameworks & References

Empirical methodology draws on:

- J-PAL South Asia empirical playbook — hypothesis testing, effect-size reporting, and confounder analysis

- Pratham's Teaching at the Right Level (TaRL) evidence base — benchmarks for remedial teaching effect sizes

- 3ie Evidence Gap Maps — for contextualising intervention effect sizes in Indian primary education

- IRIS+ indicator framework — for outcome indicator selection

Data sources:

- Synthetic dataset generated to match distributional properties of ASER (Pratham), UDISE+, and HMIS benchmarks for Rajasthan primary schools

- District-level characteristics calibrated against Census 2011 and NFHS-5 district fact sheets

Tools:

- Python 3.12 — pandas, statsmodels, numpy (data generation & regression)

- openpyxl — Excel workbook generation

- docx (Node.js) — this report

End of Report  |  Challenge 5.3 — Data-Driven Optimisation of a Social Program